## Sheet1
Tourism Awards Gala Dinner
TIME | LOCATION | ACTIVITY | LEAD | INSTRUCTIONS | CONTACT
Saturday, Sept. 24, 2022-Event Day
10:30 | Loading Dock | Ensures tables and event areas are styled and set up by 4:00 PM. | Officer James | Confirms event requirements. | Style Is Us (Decor) - 0422 222 222
Event Officer James meets AV techs from Pro AV at the stage.
12:20 | Stage |  | Officer James | Confirms final set-up and sound check is completed. | Pro AV (Audio/Visual) - 0433 333 333
12:30 | Eatons Hill Hotel Grand Ballroom | Bay Band arrives at the venue with two vans | Stage Manager Sam | Stage staff will be on standby to assist with unloading equipment if needed. | Bay Band - Chris (Leader) - 0441 111 111 (2 vans)
13:00 | stage. | Bay Band begins set-up and sound check on stage |  | AV techs will be available to assist the band | Pro AV (Audio/Visual) - 0433 333 333
18:00 | Eatons Hill Hotel Grand Ballroom | Guests begin to arrive | Officer James
18:10 | Stage | Mayor delivers a "Welcome Address" speech. | Mandy (MBRC) |  | Mandy (MBRC) - 0477 777 777
18:20 | Stage | CEO delivers a speech on "Tourism Outlook and Opportunities in our Region." | Mandy (MBRC) |  | Mandy (MBRC) - 0477 777 777
18:40 | Stage | Mayor presents awards on stage | Sam (MBRC) |  | Sam (MBRC) - 0498 989 898
19:00 |  | Bay Band performance begins. |  | Dance floor opens
20:00 |  | Peak performance time for Bay Band. | Bay Band - Chris (Leader) |  | Bay Band - Chris (Leader) - 0441 111 111 (2 vans)
22:30 |  | Bay Band's performance ends. |  | AV techs begin playing house music (as instructed by Stage Manager Sam | James (MBRC) - Event Officer
House lights are turned up (as instructed by Stage Manager Sam)
23:00 |  | Bay Band's performance ends. |  | Bay Band begins packing up equipment
0:00 |  | Pack-up equipment |  | All personnel and vendors depart the venue
Event Date: Saturday, Sept. 24, 2022
Event Time: 5:30 p.m. arrival for a 6 p.m. start to 11 p.m.
Event Location: Eatons Hill Hotel Grand Ballroom
Event Organiser and Contact No.: Mandy – Event Supervisor/Manager – 0477 777 777